DEPI | Digital Egypt Pioneers Initiative

DEPI Project Plan

Project 4: SIEM Detection Engineering, Alert Triage & SOC Operations

1. Project Overview

| Track | Cyber Security Incident Response Analyst | Instructor | Shehab El-Batal |
| --- | --- | --- | --- |
| Team Leader | Diaa Yusuf Bedair (team of 5) | Platform | Wazuh SIEM (4-week project) |

2. Timeline (Gantt Chart)

| # | Task | Owner(s) | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week 1 – SIEM Architecture & Log Onboarding |  |  |  |  |  |  |  |  |  |  |
| 1.1 | SIEM architecture & data source inventory | Diaa, Abdullah |  |  |  |  |  |  |  |  |
| 1.2 | Wazuh agents, log forwarding & onboarding | Samar, Ahmed |  |  |  |  |  |  |  |  |
| 1.3 | Field mapping & retention plan | Samar, Asmaa |  |  |  |  |  |  |  |  |
| Week 2 – Correlation Rules & Detection Use Cases |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Rules: brute force, login, lateral movement | Ahmed |  |  |  |  |  |  |  |  |
| 2.2 | Rules: persistence & data exfiltration | Abdullah |  |  |  |  |  |  |  |  |
| 2.3 | Controlled test scenarios & event generation | Samar |  |  |  |  |  |  |  |  |
| 2.4 | Testing, tuning & use-case document | Ahmed, Abdullah, Asmaa |  |  |  |  |  |  |  |  |
| Week 3 – Dashboards, Metrics & Alert Triage |  |  |  |  |  |  |  |  |  |  |
| 3.1 | SOC dashboard & KPI definitions | Abdullah |  |  |  |  |  |  |  |  |
| 3.2 | Triage of 3+ sample alerts | Samar, Asmaa |  |  |  |  |  |  |  |  |
| 3.3 | Escalation communication & asset context | Asmaa |  |  |  |  |  |  |  |  |
| 3.4 | Rule refinement from triage feedback | Ahmed |  |  |  |  |  |  |  |  |
| Week 4 – Threat Intelligence, SOAR & AI-Assisted SOC Workflow |  |  |  |  |  |  |  |  |  |  |
| 4.1 | IOC enrichment & MITRE ATT&CK map | Asmaa |  |  |  |  |  |  |  |  |
| 4.2 | SOAR playbook (phishing / malware) | Diaa |  |  |  |  |  |  |  |  |
| 4.3 | Ollama triage workflow & validation | Abdullah, Ahmed |  |  |  |  |  |  |  |  |
| 4.4 | Final SOC operations report | Diaa (all members) |  |  |  |  |  |  |  |  |
| Milestones (M0–M4, see Section 3) |  |  | M0 | M1 |  | M2 |  | M3 |  | M4 |

3. Milestones

| ID | Milestone | Target | Completion Criteria | Owner(s) |
| --- | --- | --- | --- | --- |
| M0 | Project Kickoff | Start of Week 1 | Roles assigned; repository set up; scope agreed. | Diaa |
| M1 | SIEM Foundation | End of Week 1 | SIEM architecture defined and logs onboarded. | Diaa, Samar |
| M2 | Rules Validated | End of Week 2 | 5–10 rules tested, tuned, and documented. | Ahmed, Abdullah |
| M3 | SOC Visibility Ready | End of Week 3 | Dashboard, KPIs, and 3+ triage reports ready. | Abdullah, Asmaa |
| M4 | Final Delivery | End of Week 4 | All deliverables done; final report submitted. | Diaa + team |

4. Deliverables

| # | Deliverable | Week | Owner(s) | Format / Evidence |
| --- | --- | --- | --- | --- |
| 1 | SIEM architecture diagram | W1 | Diaa | Diagram (PNG/PDF) in repository |
| 2 | Data source inventory | W1 | Diaa, Abdullah | Table of sources, log types, and onboarding status |
| 3 | Log onboarding evidence | W1 | Samar, Ahmed | Wazuh screenshots and configuration files |
| 4 | Normalized field mapping | W1 | Samar | Table mapping raw log fields to normalized fields |
| 5 | Log retention plan | W1 | Asmaa | Short document |
| 6 | 5–10 correlation rules | W2 | Ahmed, Abdullah | Wazuh rule files (XML) and pseudocode |
| 7 | Detection use-case document | W2 | Asmaa, Ahmed | Purpose, data, and logic per use case |
| 8 | Tuning notes & test results | W2 | Samar, Ahmed, Abdullah | Test log with false positive / negative notes |
| 9 | SOC dashboard screenshots | W3 | Abdullah | Screenshots of Wazuh dashboards |
| 10 | KPI definitions | W3 | Abdullah | KPI table: MTTD, MTTR, volume, closure rate |
| 11 | Triage reports (3+ alerts) | W3 | Samar, Asmaa | Structured reports with escalation message |
| 12 | Threat intelligence report | W4 | Asmaa | Report of enriched IOCs and asset context |
| 13 | MITRE ATT&CK coverage map | W4 | Asmaa | Technique mapping of detected activity |
| 14 | SOAR response playbook | W4 | Diaa | Decision points for phishing / malware scenario |
| 15 | AI-assisted triage workflow | W4 | Abdullah, Ahmed | Ollama prompts and validation notes |
| 16 | Final SOC operations report | W4 | Diaa (all members) | Technical and executive-level report |

5. Resource Allocation

5.1 Team Allocation

| Member | Role | Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- | --- | --- |
| Diaa Yusuf Bedair | Team Leader, Project Coordinator | SIEM architecture; data source inventory; repository setup | Coordinate testing; review documentation | Review triage reports and dashboard | SOAR playbook; final SOC operations report |
| Samar Eid Abdelazeem | Log Onboarding Engineer | Wazuh agents, log forwarding, field mapping | Generate controlled test events; support tuning | Alert triage and investigation reports | Collect evidence for the final report |
| Ahmed Mohamed Effat | Detection Engineer | Support log onboarding; review log coverage | Brute force, login, and lateral movement rules; tuning | Refine rules from triage feedback | Ollama workflow and manual validation |
| Abdullah Ashraf Mahmoud | Detection & Dashboard Engineer | Support data source inventory | Persistence and exfiltration rules; tuning | SOC dashboard and KPI definitions | Ollama workflow and manual validation |
| Asmaa Shokry Salah | Threat Intelligence & Triage Analyst | Retention plan; support field mapping | Use-case document; test documentation | Alert triage; escalation; asset context | IOC enrichment and MITRE ATT&CK coverage map |

Proposed allocation; the final distribution may be adjusted according to the practical implementation workload.

5.2 Tools & Resources

| Resource | Purpose |
| --- | --- |
| Wazuh (manager, agents, dashboard) | Central SIEM: log collection, rules, alerts, and dashboards |
| Ollama | Local AI for alert summaries and report drafting (validated manually) |
| MITRE ATT&CK | Mapping detected activity to adversary techniques |
| Threat intelligence sources | IOC enrichment for IP addresses, domains, and other indicators |
| Lab endpoints and log sources | Telemetry for rule development, test scenarios, and triage |
| GitHub repository | https://github.com/DEPIIRTEAM/DEPI_PROJECT4 – version control and evidence storage |
| Instructor: Shehab El-Batal | Guidance and review of deliverables |