DEPI | Digital Egypt Pioneers Initiative

DEPI Risk Assessment & Mitigation Plan

Project 4: SIEM Detection Engineering, Alert Triage & SOC Operations

1. Purpose & Approach

This plan identifies the main risks to Project 4, rates each one by likelihood and impact, and defines how the team will reduce it and how it will respond if it happens. The risks are reviewed every week during the four-week project.

How risks are managed

| Activity | When | Description |
| --- | --- | --- |
| Weekly review | End of each week | The team leader reviews each risk with its owner and updates likelihood, impact, and status. |
| Escalation | When a High risk happens | The team informs the instructor (Shehab El-Batal) and agrees on the contingency action. |
| Closure | Week 4 | Remaining risks and lessons learned are summarized in the final SOC operations report. |

2. Rating Scale

| Level | Likelihood | Impact |
| --- | --- | --- |
| Low (1) | Unlikely during the four weeks | Small delay; deliverables are not affected |
| Medium (2) | May happen during the project | Delays or reduces one deliverable |
| High (3) | Likely to happen | Threatens a milestone or a key deliverable |

Rating = Likelihood × Impact:  1–2 Low   |   3–4 Medium   |   6–9 High

3. Risk Matrix

| Impact \ Likelihood | Low (1) | Medium (2) | High (3) |
| --- | --- | --- | --- |
| High (3) | R12 R13 | R01 R02 R03 R08 | – |
| Medium (2) | – | R05 R07 R09 R10 R11 | R04 |
| Low (1) | – | R06 | – |

Each cell lists the risk IDs from the register. Green = Low, amber = Medium, orange = High.

4. Risk Register

| ID | Risk | Likelihood | Impact | Rating | Mitigation (prevent / reduce) | Contingency (if it happens) | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Technical |  |  |  |  |  |  |  |
| R01 | Wazuh deployment or agent connectivity problems delay log onboarding | Medium | High | High (6) | Start deployment on day 1 of Week 1; follow the official Wazuh documentation; keep a configuration backup. | Fall back to a simpler single-node setup and onboard fewer sources first. | Samar |
| R02 | Lab hardware (CPU, RAM, storage) is not enough for Wazuh, endpoints, and Ollama | Medium | High | High (6) | Check resource needs in Week 1; use lightweight endpoints; limit log volume and retention. | Run heavy tasks at different times; use a smaller Ollama model. | Diaa |
| R03 | Collected logs lack the data needed for some use cases (e.g., lateral movement, exfiltration) | Medium | High | High (6) | List the telemetry each use case needs in Week 1; enable extra endpoint logging early. | Adjust the use case to the available telemetry and document the limitation. | Ahmed |
| R04 | Rules produce too many false positives or miss events | High | Medium | High (6) | Test every rule with controlled scenarios; tune thresholds and time windows; record tuning notes. | Narrow or disable noisy rules and keep the most reliable ones in the final set. | Ahmed, Abdullah |
| R05 | Test scenarios are unrealistic or cannot be generated safely | Medium | Medium | Medium (4) | Use controlled scenarios inside an isolated lab only; prepare them before Week 2. | Replay sample logs or simulate the events instead. | Samar |
| R06 | Threat intelligence sources are limited (rate limits, no access) | Medium | Low | Low (2) | Prepare more than one free source; save enrichment results. | Do manual lookups for the sample alerts. | Asmaa |
| R07 | Ollama gives inaccurate or slow output on lab hardware | Medium | Medium | Medium (4) | Use AI only for summaries and drafts; validate every output manually against the evidence. | Use a smaller model or write the affected parts manually. | Abdullah, Ahmed |
| Project Management |  |  |  |  |  |  |  |
| R08 | The tight four-week schedule causes cascading delays | Medium | High | High (6) | Track weekly milestones; keep core tasks in the first half of each week; review progress weekly. | Reduce optional work and focus on the required deliverables. | Diaa |
| R09 | Uneven workload or a team member becomes unavailable | Medium | Medium | Medium (4) | Assign a co-owner to each main task; keep shared documents in the repository. | Redistribute tasks at the weekly review. | Diaa |
| R10 | Scope grows beyond the plan (extra use cases or integrations) | Medium | Medium | Medium (4) | Freeze the scope after Week 1; keep extra ideas in a backlog. | Drop additions that threaten milestones; ask the instructor if unsure. | Diaa |
| R11 | Documentation is incomplete or inconsistent at the end | Medium | Medium | Medium (4) | Document while working; use the deliverables checklist; review in the first half of Week 4. | Assign one member to consolidate and edit all documents. | Diaa, Asmaa |
| Security & Data Handling |  |  |  |  |  |  |  |
| R12 | Work or configuration is lost (VM failure, no backup) | Low | High | Medium (3) | Push rules, configs, and documents to GitHub; take VM snapshots after major steps. | Restore from the latest snapshot or repository version. | Samar, Diaa |
| R13 | Sensitive data (credentials, real IPs) is exposed in the repository or screenshots | Low | High | Medium (3) | Use lab data only; remove secrets and hide real identifiers before committing or sharing. | Replace the exposed files and change any exposed credentials. | Diaa |